## Project Information
Intro to a Lawfirm
Project Lead | Amanda Koski
Project Start | 2021-10-11
PROJECT INFORMATION
Project Information | A need arose for incoming employees to learn about the inner workings of a lawfirm. The request originally came from FG, but has since morphed into a general class for all incoming employees with little to no law firm experience. This module is going to be offered to incoming employees and will breakdown how a lawfirm works, the different departments within a lawfirm, and general business information.
Developer(s) | Amanda Koski - Lead eLearning developer EG - SME and script creation HR LD Team - support and review
Subject Matter Expert(s) | EG, Amanda Koski, & HK (Legal side)
Stakeholder(s) | EG & NC
PROJECT MILESTONES
Script/Storyboard | 2021-10-13
Audio Recording | 2021-11-18
Visual Creation | 2021-11-18
Final Review | 2021-12-03
COURSE INFORMATION
Course Name | Introduction to a Lawfirm
Course Purpose | To give new employees introductory information on how Foley operates, including information on the different departments, people at Foley & Lardner, and general lawfirm jargon.
Target Learners | The target audience is staff new hires with little to no experience working in a lawfirm, however this course will be required all incoming staff.
Learning Objectives | Define the departments within the lawfirm and describe their functions in relationship to one another.
Summarize the billing process from beginning to end with an emphasis on how a lawfirm makes its money. Which includes defining billable and non-billable hours, the client recruitment process, and what a "partner" is and how they work within the firm.
Recognize the various members of the leadership team and their roles within the firm.
Project Deliverables | Training video - roughly 5 min long with icon animation and Foley Leadership images. eLearning Module to house training video along with a glossary and minimal interactions.
COURSE DEVELOPMENT
Learning Content | EG will provide a script for the audio portion of the video. Amanda will work with EG to turn the script into a storyboard for video creation.
Course Reviewers | HR LD Team HK
Project Constraints | The project will hinge on availability of AK, the speed in which the HR LD Team can review and provide timely feedback, and the Legal Review's availability to review.
Success Measurement | The end user will succesffuly complete the course in iLearn when they have watched 80% of the video.
OTHER INFORMATION
Other Information | After video creation, EG will monitor any changes in leadership and alert the Learning Design Team with a ticket to update the video.
*This is a real project plan for an ongoing project. Names have been abreviated and changed for privacy of those involved.

## Project Schedule
Intro to a Lawfirm
Amanda Koski
| Project Start: |  | 2021-10-11
| Display Week: |  | 1 |  |  | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31
 | time axis 2021-10-11 to 2022-02-06
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-10-11 to 2022-02-06
Script/Storyboard |  |  | 2021-10-13 | 2021-11-18 | 37
Script Creation | EG |  | 2021-10-13 | 2021-10-22 | 10
Glossary Creation | EG |  | 2021-10-13 | 2021-10-22
Review | HR LD |  | 2021-10-25 | 2021-11-05 | 12
Storyboard Creation | AK |  | 2021-11-08 | 2021-11-17 | 10
EG & AK Review | EG/AK |  | 2021-11-17 | 2021-11-18 | 2
Audio Recording |  |  | 2021-11-18 | 2021-11-30 | 13
Audio Recording | AK |  | 2021-11-18 | 2021-11-25 | 8
Thanksgiving | - |  | 2021-11-25 | 2021-11-26
Audio Editing | AK |  | 2021-11-25 | 2021-11-30 | 6
Visual Creation |  |  | 2021-11-18 | 2021-12-16 | 29
Gather Foley Images | EG |  | 2021-11-18 | 2021-11-30 | 13
Import Audio | AK |  | 2021-12-01 | 2021-12-02 | 2
Gather Visuals (Icons) | AK |  | 2021-12-03 | 2021-12-16 | 14
Final Review |  |  | 2021-12-03 | 2021-01-11 | -325
First Draft | AK |  | 2021-12-03 | 2021-12-16 | 14
Review & Test | HR LD |  | 2021-12-17 | 2021-12-22 | 6
Amanda OOO | AK |  | 2021-12-22 | 2022-01-02
Final Draft | AK |  | 2022-01-03 | 2022-01-05 | 3
Final Review | EG |  | 2022-01-06 | 2022-01-07 | 2
Import Final Version to iLearn | AK |  | 2022-01-10 | 2022-01-11 | 2
Insert new rows ABOVE this one